## Citation Tracker
Priority | Platform | Current Address Listed | Phone Issue | URL to Update | How to Update | Deadline | Status | Notes
P1 | Google Business Profile | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct |  | Search 'Google Business Profile' > Edit > Update address | Apr 1 | Completed | MOST IMPORTANT - update on move day
P1 | Yelp | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://biz.yelp.com | Log in to Yelp for Business > Edit Business Info | Apr 1 | Completed
P1 | Apple Maps (Apple Business Connect) | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://businessconnect.apple.com | Claim/update via Apple Business Connect | Apr 1 | Completed
P1 | Bing Places | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://www.bingplaces.com | Log in > Edit listing > Update address | Apr 1 | Completed
P2 | Facebook Page | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct |  | Page Settings > Edit Page Info > Address | Apr 3 | Completed
P2 | Instagram Business | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct |  | Edit Profile > Business Address | Apr 3 | Completed
P2 | Nextdoor Business Page | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct |  | Business dashboard > Edit profile | Apr 3 | Not Started
P2 | Waze | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct |  | Update via Google Business Profile (syncs) | Apr 3 | Not Started | Usually syncs from GBP
P3 | Yellow Pages (YP.com) | 1911 Fremont Ave, South Pasadena, CA 91030 | WRONG: (626) 441-8002 | https://www.yellowpages.com | Claim listing > Update address + phone | Apr 7 | Not Started | Phone number is WRONG - fix ASAP
P3 | Superpages | 1911 Fremont Ave, South Pasadena, CA 91030 | WRONG: (626) 441-8002 | https://www.superpages.com | Claim listing > Update (syncs with YP) | Apr 7 | Not Started | Phone number is WRONG
P3 | MapQuest | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://www.mapquest.com | Submit update request | Apr 7 | Not Started
P3 | Foursquare | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://foursquare.com | Claim venue > Edit details | Apr 7 | Not Started | Feeds data to Uber, Twitter, etc.
P3 | Pawlicy Advisor | 1911 Fremont Ave, South Pasadena, CA 91030 | WRONG: Lists wrong # | https://www.pawlicy.com | Contact support to update listing | Apr 7 | Not Started | Phone number is WRONG
P3 | PetDesk | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct |  | Contact PetDesk support or update in app | Apr 7 | Not Started
P4 | Healthgrades (for vets) | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct |  | Claim profile > Update | Apr 14 | Not Started
P4 | Vitals.com | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct |  | Claim profile > Update | Apr 14 | Not Started
P4 | Manta | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://www.manta.com | Claim listing > Update | Apr 14 | Not Started
P4 | Hotfrog | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://www.hotfrog.com | Add/claim business > Update | Apr 14 | Not Started
P4 | Chamberofcommerce.com | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct |  | Submit update request | Apr 14 | Not Started
P4 | BBB (Better Business Bureau) | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://www.bbb.org | Contact BBB to update listing | Apr 14 | Not Started
P5 | Data Axle (Infogroup) | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://www.dataaxle.com | Submit update - feeds 100+ directories | Apr 7 | Not Started | UPDATE EARLY - cascades to many sites
P5 | Neustar/Localeze | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://www.neustarlocaleze.biz | Submit update - major data aggregator | Apr 7 | Not Started | UPDATE EARLY - cascades
P5 | Factual (Foursquare) | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://foursquare.com | Same as Foursquare - submit correction | Apr 7 | Not Started | Merged with Foursquare
P5 | Acxiom | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct |  | Submit via their portal | Apr 14 | Not Started
P5 | Angie's List | 1911 Fremont Ave, South Pasadena, CA 91030 | Correct | https://www.angi.com | Claim/update business profile | Apr 14 | Not Started | Now called Angi
SUMMARY
Total Listings: | 25
Completed: | 6
In Progress: | 0
Not Started: | 19
Completion %: | 24%